## Sheet1
Sprint Number | Task Description | Definition of Done (DoD) | Assigned To | Hrs Planned | Hrs Spent | Date Completed | % Complete | Notes
1 | Sound Bytes | 5 sound bytes | Henry | 3 hours
1 | Images | 10 images | Janet | 4 hours
1 | Starting Base Code | Creating 2 activities | Ben | 2 hours
1 | Building Questions | 20 questions | Henry | 3 hours
1 | Setting Up Github | Respository is ready | Janet | 2 hours | 1hr | 2013-11-18 | 100% | Had to review the process of creating repositories and cloning to your computer
1 | Setting Up Layout | Receiving Mockups | Ben | 4 hours
1 | Start Screen Mockup | Final Version | Janet | 2 hours
1 | Game Screen Mockup | Final Version | Ben | 3 hours
1 | Next Level Screen Mockup | Final Version | Janet | 2 hours
1 | Game Over Screen Mockup | Final Version | Henry | 3 hours
1 | Sprint Template | Ready for Github Submittal | Henry | 1 hour |  | 2013-11-18 | 100%